## Master Execution
PETROVA 300K — MASTER EXECUTION & CERTIFICATION TABLE (ALL-IN-ONE)
Jay Pechnarai ¦ 30 Tasks ¦ 7 Tech Stacks ¦ 3 Certifications ¦ Target: $300K+ Data Engineering
ID | Phase | Task | Tech Stack | Input → Output | Status | Day | Cert Refs | Cert % | PETROVA File | Priority | Notes
PHASE 0: FOUNDATION & INFRASTRUCTURE (Day 1-3)
T01 | P0 | Repo + Git setup | Git, GitHub, VS Code | Local code → GitHub repo live | Done | D1 | DBT-01 | 100% | README.md, .github/workflows/ci.yml | P0 | github.com/Kepler22j/petrova-pipeline
T02 | P0 | dbt project init + models | dbt-core, dbt-snowflake | SQL → staging/intermediate/marts | Done | D1 | DBT-01 | 100% | dbt/models/ (20+ files) | P0 | Seeds, snapshots, macros included
T03 | P0 | Airflow Docker setup | Docker, Airflow, Postgres | YAML → running containers | In Progress | D2 | AF-03 | 70% | airflow/docker-compose.yml, Dockerfile | P0 | PySpark + Jupyter included
T04 | P0 | DAG creation (3-Gate) | Airflow, Python | Python → validated DAG workflow | Done | D2 | AF-01 | 90% | airflow/dags/petrova_validated_pipeline.py | P0 | BranchPythonOperator for gates
T05 | P0 | PySpark local environment | PySpark, Delta Lake, Docker | Docker → Jupyter + Spark cluster | In Progress | D2 | DBK-01 | 60% | airflow/docker-compose.yml (jupyter-spark) | P0 | Port 8888 + 4040 Spark UI
PHASE 1: DATA ENGINEERING CORE (Day 4-10)
T06 | P1 | Snowflake warehouse + DDL | Snowflake | Account → warehouses, schemas, tables | Done | D4 | SNF-01 | 90% | snowflake/ddl/01-06 (6 files) | P1 | DEV/PROD/ETL warehouses
T07 | P1 | Semi-structured data (VARIANT) | Snowflake | JSON/Parquet → VARIANT queries | Done | D4 | SNF-01 | 95% | snowflake/ddl/07_semi_structured.sql | P1 | FLATTEN, dot notation, ARRAY funcs
T08 | P1 | Streams + CDC | Snowflake | Table changes → CDC stream | Done | D4 | SNF-03 | 90% | snowflake/ddl/08_streams.sql | P1 | Standard + append-only + Tasks
T09 | P1 | Time Travel + Fail-safe | Snowflake | Historical queries → recovery | Done | D5 | SNF-03 | 95% | snowflake/ddl/09_time_travel.sql | P1 | AT/BEFORE/OFFSET, UNDROP, transient
T10 | P1 | Data Sharing + Security | Snowflake | RBAC + masking + network policies | Done | D5 | SNF-02 | 85% | snowflake/ddl/10_data_sharing_security.sql | P1 | Shares, masking, row access, encryption
T11 | P1 | RBAC 4-role hierarchy | Snowflake | SQL → role grants + future grants | Done | D6 | SNF-02 | 95% | snowflake/rbac/roles_and_grants.sql | P1 | READER→ANALYST→ENGINEER→ADMIN
T12 | P1 | UDFs (SQL/JS/Python) | Snowflake | Functions → reusable UDFs | Done | D6 | SNF-04 | 80% | snowflake/procedures/udf_examples.sql | P1 | Scalar, UDTF, Secure UDF
T13 | P1 | Stored Procedures | Snowflake | SQL → MERGE + immutability check | Done | D6 | SNF-04 | 85% | snowflake/procedures/sp_*.sql (2 files) | P1 | Gold MERGE + 7 Commandments
T14 | P1 | dbt testing + quality | dbt, Great Expectations | Rules → schema/custom tests | Done | D7 | DBT-02 | 90% | dbt/models/*/_schema.yml, great_expectations/ | P1 | GE checkpoint + dbt tests
T15 | P1 | Storage integration (Azure) | Snowflake, Azure | ADLS → Snowflake stages | Pending | D8 | SNF-01 | 40% | snowflake/ddl/06_stages_and_tasks.sql | P1 | Needs Azure subscription
T16 | P1 | dbt + Airflow integration | Airflow, dbt | DAG triggers → dbt run/test | Pending | D8 | AF-02/DBT-03 | 50% | airflow/dags/petrova_validated_pipeline.py | P1 | BashOperator calls dbt CLI
PHASE 1.5: PYSPARK & DATABRICKS (Day 8-12)
T17 | P1.5 | PySpark Bronze ingest | PySpark, Delta Lake | Raw files → Bronze Delta tables | Done | D8 | DBK-01 | 85% | databricks/notebooks/01_bronze_ingest.py | P1 | Auto Loader, schema inference, complex types
T18 | P1.5 | Structured Streaming + CDF | PySpark, Delta Lake | Stream → Silver Delta + CDF | Done | D9 | DBK-02 | 80% | databricks/notebooks/02_structured_streaming.py | P1 | Watermarks, triggers, Change Data Feed
T19 | P1.5 | Delta Live Tables (DLT) | Databricks DLT | Notebooks → DLT pipeline | Done | D9 | DBK-03 | 75% | databricks/dlt/petrova_dlt_pipeline.py | P1 | @dlt.table, expectations, medallion
T20 | P1.5 | Unity Catalog + governance | Databricks SQL | Catalog → schemas + grants | Done | D10 | DBK-04 | 85% | databricks/unity_catalog/setup.sql | P1 | 3-level namespace, managed vs external
T21 | P1.5 | Databricks Workflows | Databricks | Tasks → multi-step workflow | Done | D10 | DBK-05 | 70% | databricks/workflows/petrova_workflow.json | P1 | Job clusters, dependencies, cron
T22 | P1.5 | PySpark local testing | PySpark, Jupyter, Docker | Notebooks → local Spark execution | Pending | D11 | DBK-01 | 30% | jupyter-spark container (port 8888) | P1 | Run 01/02 notebooks on local Spark
T23 | P1.5 | Delta Lake OPTIMIZE/VACUUM | PySpark, Delta Lake | Tables → optimized + vacuumed | Pending | D11 | DBK-02 | 40% | databricks/unity_catalog/setup.sql L74-75 | P1 | Z-ORDER, retention, time travel
PHASE 2: END-TO-END PIPELINE & VISUALIZATION (Day 12-16)
T24 | P2 | End-to-end pipeline run | Full stack | Raw → Bronze → Silver → Gold | Pending | D12 | ALL | 60% | All folders orchestrated by Airflow | P2 | Complete medallion flow
T25 | P2 | Monitoring + alerting | Snowflake, PagerDuty | Logs → alerts + notifications | Pending | D13 | SNF-04 | 30% | monitoring/sp_pipeline_notification.sql | P2 | Resource monitors + PagerDuty
T26 | P2 | Streamlit dashboard | Streamlit, Snowpark | Gold tables → interactive UI | Pending | D14 | SNF-05 | 20% | dashboards/streamlit/app.py | P2 | 4-page app with KPIs
T27 | P2 | Data quality (GX suite) | Great Expectations | Data → validation reports | Pending | D14 | DBT-02 | 30% | great_expectations/ (3 files) | P2 | Bronze checkpoint + sensor suite
T28 | P2 | Terraform IaC | Terraform | HCL → Azure + Snowflake infra | Pending | D15 | AF-03 | 40% | terraform/ (3 files) | P2 | Dev/prod workspaces
PHASE 3: PORTFOLIO & CERTIFICATION (Day 16-21)
T29 | P3 | README + architecture docs | Markdown, SVG | Project → recruiter-ready docs | Done | D16 | ALL | 80% | README.md, docs/architecture/ | P3 | Badges, tree, quick start
T30 | P3 | CI/CD pipeline | GitHub Actions | Push → lint + test + validate | Done | D16 | AF-03 | 70% | .github/workflows/ci.yml | P3 | SQLFluff + dbt + Terraform
T31 | P3 | Interview talking points | Markdown | Experience → structured answers | Done | D17 | ALL | 60% | docs/interview_prep/talking_points.md | P3 | STAR format for each component
T32 | P3 | Resume + LinkedIn branding | Docs | Project → CV + profile | Pending | D18 | ALL | 30% | (External: LinkedIn, resume.docx) | P3 | GitHub link in Featured section
T33 | P3 | SnowPro Core exam prep | Snowflake | Study → certification | In Progress | D17-19 | SNF-01-05 | 20% | PETROVA_Study_Guide.xlsx | P3 | Week 1-2 of roadmap
T34 | P3 | Databricks DE Associate prep | Databricks, PySpark | Study → certification | Pending | D19-21 | DBK-01-05 | 15% | PETROVA_Study_Guide.xlsx | P3 | Week 3-4 of roadmap
T35 | P3 | dbt Analytics Engineer prep | dbt | Study → certification | Pending | D21+ | DBT-01-03 | 10% | PETROVA_Study_Guide.xlsx | P3 | Week 5-6 of roadmap
TOTALS

## Cert Coverage Map
CERTIFICATION → PETROVA FILE MAPPING
Cert ID | Certification | Exam Domain | PETROVA Tasks | Files Covering It | Coverage | Gap Action
SNF-01 | SnowPro Core | Architecture & Features (~20%) | T06,T07,T15 | snowflake/ddl/01-07 | 90% | Add Azure storage integration demo
SNF-02 | SnowPro Core | Access Control & Security (~15%) | T10,T11 | ddl/10_*, rbac/roles_and_grants.sql | 90% | Add Tri-Secret Secure example
SNF-03 | SnowPro Core | Data Movement & Transformation (~15%) | T08,T09 | ddl/08_streams, ddl/09_time_travel | 92% | Add Snowpipe example
SNF-04 | SnowPro Core | Performance & Tuning (~10%) | T12,T13,T25 | procedures/udf_*, sp_*, monitoring/ | 75% | Add clustering + query profile demo
SNF-05 | SnowPro Core | Overview & Connectivity (~5%) | T26 | dashboards/streamlit/app.py | 40% | Build Streamlit + Snowpark app
DBK-01 | Databricks DE | Lakehouse & Delta Lake (~20%) | T05,T17,T22 | notebooks/01_bronze_ingest.py | 80% | Run local PySpark tests
DBK-02 | Databricks DE | ELT & Incremental Processing (~25%) | T18,T23 | notebooks/02_structured_streaming.py | 75% | Add OPTIMIZE/VACUUM notebook
DBK-03 | Databricks DE | Delta Live Tables (~15%) | T19 | dlt/petrova_dlt_pipeline.py | 75% | Test DLT locally with expectations
DBK-04 | Databricks DE | Data Governance (~15%) | T20 | unity_catalog/setup.sql | 85% | Add lineage + audit log examples
DBK-05 | Databricks DE | Workflows & Production (~10%) | T21 | workflows/petrova_workflow.json | 70% | Add retry + alert config
DBT-01 | dbt Analytics Eng | Models & Materializations (~30%) | T01,T02 | dbt/models/ (staging, int, marts) | 95% | Add ephemeral CTE example
DBT-02 | dbt Analytics Eng | Testing & Quality (~20%) | T09,T14,T27 | dbt/*/_schema.yml, great_expectations/ | 90% | Add custom singular test
DBT-03 | dbt Analytics Eng | Deployment & Docs (~15%) | T16,T30 | docs/petrova_docs.md, _exposures.yml | 80% | Add dbt docs generate + serve
AF-01 | Airflow (Portfolio) | DAG Design & Operators | T04 | airflow/dags/petrova_validated_pipeline.py | 90% | Add sensor + trigger operators
AF-02 | Airflow (Portfolio) | Integration & Scheduling | T16 | airflow/dags/ + docker-compose.yml | 50% | Wire dbt CLI calls in DAG
AF-03 | Airflow (Portfolio) | Infrastructure & CI/CD | T03,T28,T30 | Dockerfile, terraform/, .github/ | 65% | Complete Docker startup

## Tech Stack Matrix
PETROVA 300K — TECHNOLOGY STACK MATRIX
Technology | Category | PETROVA Usage | Tasks | Docker Service | Local Port
Snowflake | Cloud DW | Medallion schema, DDL, RBAC, streams, time travel, UDFs, stored procs | T06-T13 | — | —
dbt | Transform | 20+ models (staging→intermediate→marts), macros, seeds, snapshots, tests | T02,T14,T16 | airflow container | —
Apache Airflow | Orchestration | 3-Gate validated pipeline DAG, BranchPythonOperator, scheduling | T03,T04,T16 | airflow-webserver | 8080
PySpark | Processing | Bronze ingest (Auto Loader), structured streaming, complex types, UDFs | T05,T17,T18,T22 | jupyter-spark | 8888
Delta Lake | Storage | ACID tables, CDF, OPTIMIZE, VACUUM, Z-ORDER, time travel | T17-T23 | jupyter-spark | —
Databricks DLT | Pipeline | Medallion DLT pipeline with expectations (expect/drop/fail) | T19 | — | —
Unity Catalog | Governance | 3-level namespace, managed/external tables, grants, lineage | T20 | — | —
Great Expectations | Quality | Bronze checkpoint, sensor data suite, validation reports | T14,T27 | airflow container | —
Terraform | IaC | Azure + Snowflake providers, dev/prod workspaces | T28 | — | —
Docker | Containers | Airflow + Postgres + Jupyter/Spark multi-service stack | T03,T05 | all services | —
PostgreSQL | Metadata DB | Airflow backend database | T03 | postgres | 5432
Streamlit | Dashboard | 4-page interactive app with sensor KPIs + revenue charts | T26 | — | —
GitHub Actions | CI/CD | SQLFluff linting + dbt compile + Terraform validate | T30 | — | —
Azure (ADLS) | Cloud Storage | Landing zone for raw files, Snowflake external stages | T15 | — | —
Jupyter Lab | Notebooks | Local PySpark development environment with Delta Lake | T22 | jupyter-spark | 8888
Spark UI | Monitoring | Job execution monitoring and DAG visualization | T22 | jupyter-spark | 4040