PETROVA 300K

TRIPLE CERTIFICATION ROADMAP

SnowPro Core  |  Databricks DE Associate  |  dbt Analytics Engineer

Prepared for: Jay Pechnarai (Jakapong Pechnarai)

Study Pace: 3-4 hours/day  |  Total Duration: 7 weeks

Target: $300K+ Senior/Staff Data Engineering Roles

# Table of Contents

# 1. Certification Overview

This roadmap provides a structured 7-week plan to earn three industry-recognized certifications that directly complement your PETROVA 300K portfolio project. Together, they validate your expertise across the entire modern data stack.

## 1.1 Why These Three Certifications?

| SnowPro Core (COF-C03) | Databricks DE Associate | dbt Analytics Engineer |
| --- | --- | --- |
| Validates Snowflake architecture, SQL, data loading, security, performance tuning | Validates Spark, Delta Lake, ETL pipelines, data governance on Databricks | Validates dbt modeling, testing, documentation, deployment best practices |
| Exam: 100 questions, 115 min | Exam: 45 questions, 90 min | Exam: 65 questions, 100 min |
| Cost: $175 USD | Cost: $200 USD | Cost: $200 USD |
| PETROVA Link: Snowflake DDL, RBAC, Medallion schemas, Snowpipe, procedures | PETROVA Link: Databricks target in dbt, Delta Lake, Spark transforms | PETROVA Link: 14 dbt models, 4 macros, schema tests, packages |

## 1.2 Recommended Udemy Courses

### SnowPro Core Prep

Primary: Training for Snowflake SnowPro Core Certification Exam C03 by Tom Bailey (4.6★, 12.9K ratings, 9.5 hrs, ~S$16)

Practice Tests: Snowflake SnowPro Core Certification Practice Tests by Hamid Qureshi (4.4★, 3.7K ratings, 700+ questions, ~S$20)

### Databricks DE Associate Prep

Primary: Databricks Certified Data Engineer Associate - Preparation by Derar Alhussein (4.5★, 17K ratings, Bestseller, ~S$16)

Hands-On: The Complete Snowflake & dbt Hands-On Course by Daniel Weigel (4.6★, 985 ratings, 12 hrs, ~S$14)

### dbt Analytics Engineer Prep

Primary: The Complete dbt (Data Build Tool) Bootcamp: Zero to Hero by Zoltan C. Toth (4.5★, 11.1K ratings, Bestseller, ~S$15)

Cert-Specific: The Complete dbt Certification Course by Daniel Weigel (4.8★, 78 ratings, 11 hrs, ~S$14)

Practice Tests: dbt Analytics Engineering Certification Practice Tests by Zoltan C. Toth (4.8★, 195 questions, ~S$14)

# 2. Week-by-Week Study Schedule

Total timeline: 7 weeks at 3-4 hours/day (21-28 hours/week). Each certification gets dedicated focus time with overlap for reinforcement.

## 2.1 Timeline Overview

| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 |
| --- | --- | --- | --- | --- | --- | --- |
| Snowflake Core | Snowflake Exam Prep | Databricks Core | Databricks Exam Prep | dbt Core | dbt Exam Prep | Final Review + Exams |

## Week 1: SnowPro Core – Foundations

Certification: SnowPro Core

| Day | Hours | Topics & Activities | Resources |
| --- | --- | --- | --- |
| Mon | 3.5h | Snowflake Architecture: Virtual Warehouses, Micro-partitions, Cloud Services Layer | Tom Bailey Course: Sections 1-3 |
| Tue | 3.5h | Data Loading: COPY INTO, Snowpipe, File Formats (Parquet/CSV/JSON), Stages | Tom Bailey Course: Sections 4-5 |
| Wed | 3.5h | Data Transformations: SQL, Views, Materialized Views, Streams, Tasks | Tom Bailey Course: Sections 6-7 |
| Thu | 3.5h | Semi-Structured Data: VARIANT, FLATTEN, LATERAL. Time Travel & Fail-safe | Tom Bailey Course: Sections 8-9 |
| Fri | 3h | Security: RBAC, Network Policies, Column/Row-Level Security, Encryption | Tom Bailey Course: Sections 10-11 |
| Sat | 4h | Performance Tuning: Query Profile, Clustering, Caching, Resource Monitors | Tom Bailey Course: Sections 12-14 |
| Sun | 2h | Review + PETROVA project walkthrough: map your Snowflake DDL/RBAC to exam topics | Review notes, re-read snowflake/ folder |

## Week 2: SnowPro Core – Exam Prep & Sit Exam

Certification: SnowPro Core

| Day | Hours | Topics & Activities | Resources |
| --- | --- | --- | --- |
| Mon | 3.5h | Practice Test Set 1 (Hamid Qureshi): Take first 100 questions, review wrong answers | Note weak areas |
| Tue | 3.5h | Deep dive into weak areas from Practice Test 1. Revisit Tom Bailey lectures. | Focus on bottom 2-3 topics |
| Wed | 3.5h | Practice Test Set 2: Take next 100 questions under timed conditions | Simulate exam: 115 min |
| Thu | 3.5h | Practice Test Set 3 + review. Target: consistently scoring 80%+ | Review all wrong answers |
| Fri | 3h | Final review: Snowflake documentation quick-read on exam guide topics | docs.snowflake.com |
| Sat | 2h | EXAM DAY: SnowPro Core Certification (COF-C03) | Book at webassessor.com |
| Sun | — | Rest day. Celebrate passing! | — |

## Week 3: Databricks DE Associate – Foundations

Certification: Databricks DE Associate

| Day | Hours | Topics & Activities | Resources |
| --- | --- | --- | --- |
| Mon | 3.5h | Databricks Lakehouse Architecture: Unity Catalog, Delta Lake fundamentals | Derar Alhussein Course: Sections 1-3 |
| Tue | 3.5h | ELT with Spark SQL: Querying files, transformations, complex types | Derar Course: Sections 4-5 |
| Wed | 3.5h | Incremental Data Processing: Structured Streaming, Auto Loader, Change Data Feed | Derar Course: Sections 6-7 |
| Thu | 3.5h | Delta Live Tables: Medallion Architecture in DLT, expectations, pipeline config | Derar Course: Section 8 |
| Fri | 3h | Workflows & Jobs: Multi-task jobs, job clusters, task orchestration | Derar Course: Sections 9-10 |
| Sat | 4h | Data Governance: Unity Catalog, data access control, data lineage, audit logs | Derar Course: Sections 11-12 |
| Sun | 2h | Review + PETROVA: map your Databricks dbt target profile to exam concepts | Review dbt/profiles.yml.example |

## Week 4: Databricks DE Associate – Exam Prep & Sit Exam

Certification: Databricks DE Associate

| Day | Hours | Topics & Activities | Resources |
| --- | --- | --- | --- |
| Mon | 3.5h | Practice Exam 1 (Derar Alhussein practice tests): full 45-question set | Review every wrong answer |
| Tue | 3.5h | Weak area deep dive: revisit lectures + Databricks documentation | Focus on bottom topics |
| Wed | 3.5h | Practice Exam 2: timed simulation (90 minutes) | Target: 75%+ pass rate |
| Thu | 3.5h | Hands-on lab: run through Databricks Community Edition exercises | community.cloud.databricks.com |
| Fri | 3h | Practice Exam 3 + final review of exam guide | databricks.com/learn |
| Sat | 2h | EXAM DAY: Databricks Certified Data Engineer Associate | Book at kryterion.com |
| Sun | — | Rest day. | — |

## Week 5: dbt Analytics Engineer – Foundations

Certification: dbt Analytics Engineer

| Day | Hours | Topics & Activities | Resources |
| --- | --- | --- | --- |
| Mon | 3.5h | dbt Fundamentals: Models, materializations (view, table, incremental, ephemeral) | Zoltan Toth Course: Sections 1-4 |
| Tue | 3.5h | Sources, Seeds, Snapshots. Ref function. dbt_project.yml configuration | Zoltan Toth Course: Sections 5-7 |
| Wed | 3.5h | Testing: schema tests, data tests, dbt_expectations package. dbt test command | Zoltan Toth Course: Sections 8-9 |
| Thu | 3.5h | Advanced: Jinja/Macros, custom schema generation, packages (dbt_utils) | Zoltan Toth Course: Sections 10-12 |
| Fri | 3h | Documentation: doc blocks, dbt docs generate/serve. Exposures and metrics | Zoltan Toth Course: Sections 13-14 |
| Sat | 4h | Deployment: dbt Cloud vs dbt Core, CI/CD, environments, job scheduling | Daniel Weigel Cert Course: Sections 1-5 |
| Sun | 2h | Review + PETROVA: walk through your 14 dbt models, 4 macros, schema tests | Map to exam objectives |

## Week 6: dbt Analytics Engineer – Exam Prep

Certification: dbt Analytics Engineer

| Day | Hours | Topics & Activities | Resources |
| --- | --- | --- | --- |
| Mon | 3.5h | Daniel Weigel Cert Course: remaining sections + practice exercises | Focus on dbt Cloud specifics |
| Tue | 3.5h | Practice Test Set 1 (Zoltan Toth, 65 questions): full timed simulation | Review wrong answers thoroughly |
| Wed | 3.5h | Weak area review: re-read dbt docs (docs.getdbt.com) on problem topics | dbt Discourse for edge cases |
| Thu | 3.5h | Practice Test Set 2: target 80%+ consistent pass rate | Note any remaining gaps |
| Fri | 3h | Practice Test Set 3 + review dbt Analytics Engineering exam guide | getdbt.com/certifications |
| Sat | 4h | Hands-on: modify PETROVA dbt models to cover any exam gaps found | Update your repo with improvements |
| Sun | 2h | Light review. Prepare for final exam week. | Rest and consolidate |

## Week 7: Final Review & Remaining Exams

Certification: All Three

| Day | Hours | Topics & Activities | Resources |
| --- | --- | --- | --- |
| Mon | 3.5h | dbt Certification: Final practice test + confidence check. Book exam. | Ensure 80%+ on practice |
| Tue | 2h | EXAM DAY: dbt Analytics Engineering Certification | getdbt.com/certifications |
| Wed | 3h | Update PETROVA README with certification badges. Push to GitHub. | Add cert logos/links |
| Thu | 3h | Update LinkedIn: add all 3 certifications. Update resume/portfolio. | LinkedIn Certifications section |
| Fri | 2h | Write 1-2 technical blog posts about your PETROVA architecture | Medium or dev.to |
| Sat | — | Rest. You are now triple-certified. | — |
| Sun | — | Start applying for $300K+ roles! | — |

# 3. Investment Summary

## 3.1 Course Costs

| Item | Cost (SGD) | Cost (USD est.) |
| --- | --- | --- |
| Tom Bailey - SnowPro Core Course | S$15.98 | ~$12 |
| Hamid Qureshi - SnowPro Practice Tests | S$19.98 | ~$15 |
| Derar Alhussein - Databricks DE Associate | S$15.98 | ~$12 |
| Derar Alhussein - Databricks Practice Tests | S$15.98 | ~$12 |
| Zoltan C. Toth - dbt Bootcamp (Zero to Hero) | S$14.98 | ~$11 |
| Daniel Weigel - dbt Certification Course | S$13.98 | ~$10 |
| Zoltan C. Toth - dbt Practice Tests | S$13.98 | ~$10 |
| TOTAL COURSES | ~S$111 | ~$82 |

## 3.2 Exam Fees

| Certification Exam | Fee (USD) |
| --- | --- |
| SnowPro Core (COF-C03) | $175 |
| Databricks Certified Data Engineer Associate | $200 |
| dbt Analytics Engineering Certification | $200 |
| TOTAL EXAMS | $575 |

Grand Total: ~$657 USD (~S$886) for courses + all 3 exams. ROI: These certifications typically increase data engineering offers by $30K-$80K/year.

# 4. Exam Day Tips & Strategy

## 4.1 General Strategy

1. Read every question twice before answering. Look for keywords like BEST, MOST, LEAST, NOT.

2. Eliminate obviously wrong answers first. Most exams have 1-2 clearly wrong choices.

3. Flag and revisit difficult questions. Don't spend more than 2 minutes on any single question.

4. Your PETROVA project is your secret weapon. When a question describes a scenario, think about how you implemented it.

## 4.2 PETROVA Project Advantage

You have a massive advantage over other test-takers: you have actually built a production-grade data platform. Here is how your project maps to each exam:

| SnowPro Core | Databricks DE Associate | dbt Analytics Engineer |
| --- | --- | --- |
| Your snowflake/ddl/ covers warehouses, schemas, tables, stages, tasks | Your dbt profiles.yml has Databricks target with Unity Catalog | Your 14 dbt models cover all materializations tested |
| Your snowflake/rbac/ is a real 4-role RBAC implementation | Your Medallion Architecture maps directly to DLT pipeline concepts | Your macros (scd2_merge, generate_schema_name) test Jinja knowledge |
| Your Snowpipe + COPY INTO DDL covers data loading questions | Your incremental models align with Structured Streaming concepts | Your _schema.yml with dbt_expectations covers testing |

## 4.3 Post-Certification Actions

1. Add certification badges to your GitHub README.md (badge images from each vendor).

2. Update LinkedIn with all three certifications in the Certifications section.

3. Update your resume header: "Triple-Certified Data Engineer (Snowflake + Databricks + dbt)"

4. Write 1-2 technical blog posts about your PETROVA architecture on Medium or dev.to.

5. Start applying. Target companies using Snowflake + dbt + Databricks (check job descriptions).

6. In interviews, reference both your certifications AND the PETROVA project as proof of hands-on experience.