## Master Task Tracker
PETROVA 300K — Master Task Tracker
Jay Pechnarai ¦ 19-Hour Sprint (May 16-17, 2026) ¦ Target: $300K+ Data Engineering Role
# | Time Block | Step | Task Description | Input (What You Need) | Output (Deliverable) | Why (Purpose) | Est. | Status | Notes | ✓
TODAY — DAYTIME (8 Hours: 09:00–17:00)
1 | 09:00-09:30 | Cleanup | Delete dbt/models/example/ folder & _schema_updated.yml | File Explorer open at petrova-pipeline/ | Clean repo (no leftover dbt init files) | Recruiters see only PETROVA code, not boilerplate | 30m | Pending |  | ☐
2 | 09:30-10:00 | Git | Stage, commit & push all new exam coverage files to GitHub | Clean repo + PowerShell terminal | GitHub repo updated with 85+ files at github.com/Kepler22j/petrova-pipeline | Live portfolio link for resume & LinkedIn — recruiters verify you can ship code | 30m | Pending |  | ☐
3 | 10:00-10:15 | Verify | Open GitHub repo in browser, verify all folders/files visible | Browser + GitHub URL | Confirmed: all 12 top-level dirs visible on GitHub | Catch any .gitignore issues or missing files before sharing publicly | 15m | Pending |  | ☐
4 | 10:15-10:30 | LinkedIn | Update LinkedIn headline & Featured section with GitHub repo link | LinkedIn profile + GitHub URL | LinkedIn profile shows PETROVA project link | Recruiters scan LinkedIn first — project link = instant credibility signal | 15m | Pending |  | ☐
5 | 10:30-12:30 | Study | SnowPro Core — Snowflake Overview & Architecture (Udemy Sec 1-3) | Udemy course + PETROVA snowflake/ddl/ files for reference | Notes on: virtual warehouses, micro-partitions, metadata, caching layers | Exam covers ~20% architecture questions — foundation for everything else | 2h | Pending |  | ☐
6 | 12:30-13:00 | Break | Lunch break | — | Rest & recharge | Sustained focus = better retention | 30m | — |  | —
7 | 13:00-15:00 | Study | SnowPro Core — Storage & Data Loading (Udemy Sec 4-5) | Udemy + snowflake/ddl/03-06 files | Notes on: stages, COPY INTO, file formats, VARIANT, FLATTEN | Storage/loading = ~15% of exam; your 07_semi_structured.sql covers VARIANT/FLATTEN | 2h | Pending |  | ☐
8 | 15:00-15:15 | Practice | Hands-on: Run 3 VARIANT/FLATTEN queries in Snowflake trial account | Snowflake trial + snowflake/ddl/07_semi_structured.sql | 3 working queries with JSON/array data | Doing > reading — exam has scenario-based questions requiring real experience | 15m | Pending |  | ☐
9 | 15:15-17:00 | Study | SnowPro Core — Access Control & Security (Udemy Sec 6-7) | Udemy + snowflake/ddl/10_data_sharing_security.sql + rbac/roles_and_grants.sql | Notes on: RBAC, DAC, network policies, masking, encryption hierarchy | Security = ~15% of exam; your PETROVA files already demo 4-role RBAC + masking | 1h45m | Pending |  | ☐
TONIGHT — EVENING SESSION (3 Hours: 21:00–00:00)
10 | 21:00-22:00 | Study | SnowPro Core — Performance & Tuning (Udemy Sec 8-9) | Udemy + snowflake/ddl/01_warehouse.sql | Notes on: clustering, materialized views, query profiling, resource monitors | Performance tuning = ~10% of exam; resource monitors in your 10_data_sharing_security.sql | 1h | Pending |  | ☐
11 | 22:00-23:00 | Study | Databricks DE Associate — Lakehouse & Delta Lake (Udemy Sec 1-3) | Udemy + databricks/unity_catalog/setup.sql | Notes on: Delta format, ACID, time travel, OPTIMIZE, VACUUM, Z-ORDER | Delta Lake fundamentals = ~20% of Databricks exam; your setup.sql demos all of these | 1h | Pending |  | ☐
12 | 23:00-00:00 | Review | Review Day 1 notes + create 20 flashcards (Snowflake + Delta basics) | Day's notes | 20 flashcards (physical or Anki) | Spaced repetition doubles long-term retention vs. re-reading | 1h | Pending |  | ☐
TOMORROW — FULL DAY (8 Hours: 09:00–17:00)
13 | 09:00-09:30 | Review | Morning review: re-do yesterday's 20 flashcards | Flashcards from last night | All 20 cards recalled correctly | Morning recall after sleep = strongest memory consolidation window | 30m | Pending |  | ☐
14 | 09:30-11:30 | Study | Databricks DE — ELT with Spark SQL & Python (Udemy Sec 4-6) | Udemy + databricks/notebooks/01_bronze_ingest.py | Notes on: DataFrame API, Auto Loader, COPY INTO, complex types, higher-order functions | ELT/Spark = ~25% of exam; your 01_bronze_ingest.py covers Auto Loader + complex types | 2h | Pending |  | ☐
15 | 11:30-12:30 | Study | Databricks DE — Incremental Processing & Structured Streaming (Udemy Sec 7-8) | Udemy + databricks/notebooks/02_structured_streaming.py | Notes on: readStream/writeStream, triggers, watermarks, Change Data Feed | Streaming = ~15% of exam; your 02_structured_streaming.py covers CDF + watermarks | 1h | Pending |  | ☐
16 | 12:30-13:00 | Break | Lunch break | — | Rest & recharge | Sustained focus = better retention | 30m | — |  | —
17 | 13:00-14:30 | Study | Databricks DE — Delta Live Tables & Workflows (Udemy Sec 9-10) | Udemy + databricks/dlt/petrova_dlt_pipeline.py + workflows/petrova_workflow.json | Notes on: DLT expectations, @dlt.table, pipeline modes, multi-task workflows | DLT + Workflows = ~15% of exam; your files demo full DLT pipeline + workflow JSON | 1h30m | Pending |  | ☐
18 | 14:30-15:00 | Practice | Hands-on: Create a simple DLT pipeline in Databricks Community Edition | Databricks Community Ed + petrova_dlt_pipeline.py as template | Working DLT notebook with Bronze→Silver→Gold | DLT questions are scenario-heavy — need to have actually built one | 30m | Pending |  | ☐
19 | 15:00-16:00 | Study | dbt Analytics Engineer — Models, Tests & Documentation (Udemy Sec 1-4) | Udemy + dbt/models/ + dbt/models/docs/petrova_docs.md | Notes on: ref(), source(), materializations, schema tests, doc blocks | Core dbt = ~30% of exam; your PETROVA dbt/ folder is a complete working example | 1h | Pending |  | ☐
20 | 16:00-16:30 | Study | dbt Analytics Engineer — Seeds, Snapshots & Advanced (Udemy Sec 5-7) | Udemy + dbt/seeds/ + dbt/snapshots/ + dbt/models/marts/_metrics.yml | Notes on: seeds, snapshot strategies, ephemeral, exposures, metrics, packages | Advanced dbt = ~20% of exam; your seeds/snapshots/exposures/metrics files cover all of these | 30m | Pending |  | ☐
21 | 16:30-17:00 | Review | End-of-sprint review: 20 new flashcards + practice quiz (Udemy or Whizlabs) | Day 2 notes + practice quiz site | 20 new flashcards + quiz score recorded | Self-testing reveals gaps before exam day — fix weak spots early | 30m | Pending |  | ☐
SPRINT TOTALS | [6 empty] | 19h

## Time Block Schedule
PETROVA 300K — 19-Hour Sprint Schedule
May 16-17, 2026 ¦ 3 Time Blocks ¦ Study + Build + Ship
BLOCK 1: TODAY DAYTIME
Time Window | 09:00 – 17:00
Duration | 8 Hours
Focus Areas | Repo cleanup → Git push → SnowPro Core (Architecture, Storage, Security)
BLOCK 2: TONIGHT
Time Window | 21:00 – 00:00
Duration | 3 Hours
Focus Areas | SnowPro Tuning → Databricks Delta basics → Day 1 review & flashcards
BLOCK 3: TOMORROW
Time Window | 09:00 – 17:00
Duration | 8 Hours
Focus Areas | Databricks DE deep-dive → dbt fundamentals → Final review & practice quiz
ENERGY MANAGEMENT TIPS
• Pomodoro: 50 min focus → 10 min break. Walk away from screen during breaks.
• Hands-on tasks (Git, queries) after 2h of reading to reset attention.
• Water + snack every 2 hours. Dehydration kills focus before you notice it.
• Tonight session: skip if exhausted. Sleep > cramming for long-term retention.

## Progress Dashboard
PETROVA 300K — Progress Dashboard
CERTIFICATION EXAM READINESS
Certification | Exam Code | Target Date | PETROVA Coverage | Study Progress | Practice Score | Confidence | Status
SnowPro Core | COF-C02 | Week 3 (Jun 6) | ~75% | 0% | — | — | Not Started
Databricks DE Associate | — | Week 5 (Jun 20) | ~70% | 0% | — | — | Not Started
dbt Analytics Engineer | — | Week 7 (Jul 4) | ~90% | 0% | — | — | Not Started
PETROVA PROJECT COMPLETION
Component | Files | Key Features | Quality | Status
dbt/ | 20+ | Staging→Intermediate→Marts, macros, seeds, snapshots, exposures, metrics, doc blocks | Production-ready | Done
snowflake/ | 12+ | DDL (10 files), stored procs, RBAC, VARIANT, Streams, Time Travel, UDFs | Production-ready | Done
databricks/ | 5 | Auto Loader, Structured Streaming, DLT, Workflows, Unity Catalog | Demo-ready | Done
airflow/ | 2 | Validated DAG with 3-Gate branching, Docker Compose | Demo-ready | Done
terraform/ | 3 | Azure + Snowflake providers, dev/prod workspaces | Scaffold | Done
great_expectations/ | 3 | Checkpoint + suite + config | Scaffold | Done
CI/CD (.github/) | 1 | SQLFluff + dbt compile + Terraform validate | Working | Done
docs/ | 3 | Architecture SVG, runbooks, interview talking points | Complete | Done
tests/ | 2 | Integration + E2E test files | Scaffold | Done
README.md | 1 | Full project overview with badges, tree, quick start | Recruiter-ready | Done

## Sprint Template
REUSABLE SPRINT TEMPLATE — Copy This Sheet for Each New Sprint
Sprint: __________ ¦ Date: __________ ¦ Total Hours: __________
# | Time | Category | Task | Input | Output | Why | Est. | Status
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20