## Master Summary
PETROVA 300K — MASTER EXECUTION & CERTIFICATION TABLE (ALL-IN-ONE)
Jay Pechnarai ¦ 35 Tasks ¦ 16 Technologies ¦ 3 Certifications ¦ PySpark + Delta Lake + dbt + Snowflake + Airflow
ID | Phase | Task | Tech Stack | Python/Libraries | Input | Output | Status | Day | SNF Ref | SNF % | DBK Ref | DBK % | DBT Ref | DBT % | Cert Impact % | Real-World Use Cases | Priority | Notes | ✓
PHASE 0: FOUNDATION & INFRASTRUCTURE (Day 1-3)
T01 | P0 | Repo + Git setup | Git, GitHub, VS Code | gitpython | Local code | GitHub repo live | Done | D1 | — | — | — | — | DBT-01 | 100% | 5% | Version control is standard in ALL data teams (Netflix, Uber, Airbnb) | HIGH | github.com/Kepler22j/petrova-pipeline
T02 | P0 | dbt project init + full models | dbt-core, dbt-snowflake | dbt-core, Jinja2, agate | SQL templates | 20+ staging/int/mart models | Done | D1 | — | — | — | — | DBT-01 | 100% | 12% | Spotify, JetBlue, GitLab — dbt is the standard transform layer | CRITICAL | Seeds, snapshots, macros, exposures, metrics
T03 | P0 | Airflow + PySpark Docker | Docker, Airflow, PySpark | apache-airflow, pyspark, delta-spark | YAML + Dockerfile | 4 running containers | Done | D2 | — | — | DBK-01 | 60% | — | — | 8% | Airbnb created Airflow; Uber, Lyft, Twitter all use it | CRITICAL | Docker Compose: Airflow 2.9.3 + Jupyter (quay.io) + PostgreSQL 15. All 4 containers running.
T04 | P0 | DAG creation (3-Gate) | Airflow, Python | airflow.operators, airflow.utils | Python DAG file | Validated pipeline with branching | Done | D2 | — | — | — | — | — | — | 6% | Stripe, Shopify — gate validation prevents bad data in prod | HIGH | BranchPythonOperator for gates
T05 | P0 | PySpark local environment | PySpark, Jupyter, Docker | pyspark, delta-spark, jupyter | Docker config | Spark + Delta on localhost:8888 | Done | D2 | — | — | DBK-01 | 50% | — | — | 7% | Meta, Netflix, Apple — PySpark is #1 big data processing framework | CRITICAL | Port 8888 Jupyter, 4040 Spark UI. Delta Lake 3.2.1 verified. 00_local_delta_lab.ipynb created.
PHASE 1: DATA ENGINEERING CORE — SNOWFLAKE (Day 4-7)
T06 | P1 | Snowflake warehouse + DDL | Snowflake SQL | snowflake-connector-python | Account config | 3 warehouses + 4 schemas + tables | Done | D4 | SNF-01 | 90% | — | — | — | — | 10% | Capital One, DoorDash, Adobe — Snowflake is top cloud DW | CRITICAL | DEV/PROD/ETL warehouses
T07 | P1 | Semi-structured (VARIANT) | Snowflake SQL | — | JSON/Parquet files | VARIANT queries + FLATTEN | Done | D4 | SNF-01 | 95% | — | — | — | — | 8% | Instacart, Square — JSON ingestion is daily DE work | HIGH | Dot notation, ARRAY funcs, TYPEOF
T08 | P1 | Streams + CDC | Snowflake SQL | — | Table DML changes | CDC stream + MERGE | Done | D4 | SNF-03 | 90% | — | — | — | — | 7% | Confluent, Fivetran — CDC is core to real-time pipelines | HIGH | Standard + append-only + Task pattern
T09 | P1 | Time Travel + Fail-safe | Snowflake SQL | — | Historical point | Recovered data + UNDROP | Done | D5 | SNF-03 | 95% | — | — | — | — | 6% | Snowflake unique feature — disaster recovery without backups | MEDIUM | AT/BEFORE/OFFSET, transient tables
T10 | P1 | Data Sharing + Security | Snowflake SQL | — | Security rules | Shares + masking + network policies | Done | D5 | SNF-02 | 85% | — | — | — | — | 8% | Healthcare (HIPAA), Finance (SOX) — masking is compliance req | CRITICAL | Row access, encryption hierarchy
T11 | P1 | RBAC 4-role hierarchy | Snowflake SQL | — | Role definitions | 4-role grant chain + future grants | Done | D6 | SNF-02 | 95% | — | — | — | — | 7% | Every enterprise — RBAC is interview question #1 for security | HIGH | READER→ANALYST→ENGINEER→ADMIN
T12 | P1 | UDFs (SQL/JS/Python) | Snowflake, Snowpark | snowflake-snowpark-python | Function logic | Scalar + UDTF + Secure UDF | Done | D6 | SNF-04 | 80% | — | — | — | — | 5% | Custom business logic — common in finance/IoT pipelines | MEDIUM | Python UDF via Snowpark
T13 | P1 | Stored Procedures | Snowflake SQL | — | MERGE logic | Gold MERGE + immutability check | Done | D6 | SNF-04 | 85% | — | — | — | — | 6% | ELT pattern — stored procs for Gold layer writes at scale | HIGH | 7 Commandments check + Zero-Copy Clone
T14 | P1 | dbt testing + GE quality | dbt, Great Expectations | great-expectations, dbt-core | Test rules | Schema tests + GE checkpoint | Done | D7 | — | — | — | — | DBT-02 | 90% | 8% | Notion, Canva, Deel — data quality is #1 pipeline priority | CRITICAL | Bronze checkpoint + sensor suite
PHASE 1.5: PYSPARK & DATABRICKS (Day 8-12)
T15 | P1.5 | PySpark Bronze ingest | PySpark, Delta Lake | pyspark, delta-spark | Raw files (JSON/CSV/Parquet) | Bronze Delta tables + schema inference | Done | D8 | — | — | DBK-01 | 85% | — | — | 10% | Uber (5PB/day), Netflix, LinkedIn — Auto Loader at scale | CRITICAL | Auto Loader, cloudFiles, complex types
T16 | P1.5 | Structured Streaming + CDF | PySpark, Delta Lake | pyspark.sql.streaming | Stream source | Silver Delta + Change Data Feed | Done | D9 | — | — | DBK-02 | 80% | — | — | 9% | Robinhood (real-time trades), DoorDash (live ETAs) | CRITICAL | Watermarks, triggers, _change_type columns
T17 | P1.5 | Delta Live Tables (DLT) | Databricks DLT | dlt (databricks) | Notebook code | Medallion DLT pipeline | Done | D9 | — | — | DBK-03 | 75% | — | — | 8% | Shell Energy, Columbia — DLT automates quality at scale | HIGH | @dlt.table, expect/drop/fail decorators
T18 | P1.5 | Unity Catalog + governance | Databricks SQL | — | Catalog definitions | 3-level namespace + grants + lineage | Done | D10 | — | — | DBK-04 | 85% | — | — | 8% | Comcast, ABN AMRO — UC is Databricks' governance future | HIGH | Managed vs external, Storage Credentials
T19 | P1.5 | Databricks Workflows | Databricks JSON | — | Task definitions | Multi-step workflow + scheduling | Done | D10 | — | — | DBK-05 | 70% | — | — | 5% | Condé Nast, HSBC — production job orchestration | MEDIUM | Job clusters, task dependencies, cron
T20 | P1.5 | PySpark local testing | PySpark, Jupyter, Docker | pyspark, pytest, chispa | Notebooks | Local Spark execution verified | Done | D11 | — | — | DBK-01 | 30% | — | — | 7% | Every Databricks team tests locally before deploying | HIGH | 00_local_delta_lab.ipynb: Bronze/Silver/Gold + MERGE + Time Travel + Window Fns verified locally
T21 | P1.5 | OPTIMIZE + VACUUM + Z-ORDER | PySpark, Delta Lake | delta-spark | Delta tables | Compacted + vacuumed tables | Pending | D11 | — | — | DBK-02 | 40% | — | — | 6% | Databricks best practice — prevents small file problem | MEDIUM | Z-ORDER for query perf, retention mgmt
PHASE 2: E2E PIPELINE & INTEGRATION (Day 12-16)
T22 | P2 | Storage integration (Azure) | Snowflake, Azure | azure-storage-blob | ADLS config | External stage → Snowflake | Pending | D12 | SNF-01 | 40% | — | — | — | — | 5% | Azure + Snowflake is #2 cloud combo after AWS | MEDIUM | Needs Azure subscription
T23 | P2 | dbt + Airflow integration | Airflow, dbt | apache-airflow, dbt-core | DAG + dbt CLI | Orchestrated dbt run/test | Pending | D12 | — | — | — | — | DBT-03 | 50% | 7% | Astronomer (Airflow company) + dbt Labs official pattern | HIGH | BashOperator calls dbt CLI
T24 | P2 | End-to-end pipeline run | Full stack | all packages | Raw files | Bronze→Silver→Gold complete flow | Pending | D13 | SNF-01 | 60% | DBK-01 | 60% | DBT-01 | 60% | 12% | The #1 interview question: 'walk me through your pipeline' | CRITICAL | Full medallion with all gates
T25 | P2 | Monitoring + alerting | Snowflake, PagerDuty | pagerduty-api | Logs + metrics | Alerts + resource monitors | Pending | D14 | SNF-04 | 30% | — | — | — | — | 4% | PagerDuty used by 70% of Fortune 500 for incident mgmt | MEDIUM | monitoring/sp_pipeline_notification.sql
T26 | P2 | Streamlit dashboard | Streamlit, Snowpark | streamlit, snowflake-snowpark | Gold tables | Interactive 4-page UI | Pending | D14 | SNF-05 | 20% | — | — | — | — | 5% | Snowflake acquired Streamlit — it's their official UI layer | MEDIUM | dashboards/streamlit/app.py
T27 | P2 | Terraform IaC | Terraform, Azure | — | HCL files | Provisioned infra (dev/prod) | Pending | D15 | — | — | — | — | — | — | 4% | HashiCorp standard — Snowflake Terraform provider is official | LOW | terraform/ (3 files)
PHASE 3: PORTFOLIO & CERTIFICATION (Day 16-21)
T28 | P3 | README + architecture | Markdown, SVG | — | Project docs | Recruiter-ready README + arch diagram | Done | D16 | — | — | — | — | — | — | 5% | GitHub README is the first thing a hiring manager sees | HIGH | README.md updated with Docker stack + certs. SVG revised with 10 Silver logics.
T29 | P3 | CI/CD pipeline | GitHub Actions | sqlfluff, dbt-core | Push event | Lint + compile + validate | Done | D16 | — | — | — | — | — | — | 4% | Every FAANG uses CI/CD — shows production mindset | MEDIUM | .github/workflows/ci.yml
T30 | P3 | Interview talking points | Markdown | — | Experience | STAR-format answers per component | Done | D17 | — | — | — | — | — | — | 5% | Structured answers win interviews — STAR is standard format | HIGH | PETROVA_Interview_Report.docx: 15 Q&As + weakness analysis + roadmap
T31 | P3 | Resume + LinkedIn | Docs | — | Project portfolio | Updated CV + LinkedIn Featured | Pending | D18 | — | — | — | — | — | — | 8% | LinkedIn is how 85% of DE roles are filled (LinkedIn data) | CRITICAL | GitHub link in Featured section
T32 | P3 | SnowPro Core exam | Snowflake | — | Study materials | SnowPro Core certification | In Progress | D17-19 | ALL | 75% | — | — | — | — | 15% | 175K+ SnowPro certified professionals globally | CRITICAL | PETROVA_Study_Guide.xlsx
T33 | P3 | Databricks DE Associate | Databricks, PySpark | pyspark | Study materials | Databricks DE certification | Pending | D19-21 | — | — | ALL | 70% | — | — | 12% | 100K+ Databricks certified; fastest growing cert in data | CRITICAL | PETROVA_Study_Guide.xlsx
T34 | P3 | dbt Analytics Engineer | dbt | dbt-core, Jinja2 | Study materials | dbt Analytics Eng certification | Pending | D21+ | — | — | — | — | ALL | 90% | 10% | dbt community: 50K+ members, 9K+ companies use dbt | HIGH | PETROVA_Study_Guide.xlsx
SPRINT TOTALS

## Cert Detail & Links
CERTIFICATION DOMAINS — Detail + Exam Links + Real-World Companies
Cert ID | Certification | Exam Domain | Exam Weight | PETROVA Coverage | Gap | Exam Link | Famous Companies Using This | Impact
SNF-01 | SnowPro Core | Architecture, Storage & Data Loading | ~35% | 90% | Add Snowpipe + Azure integration | https://learn.snowflake.com/en/certifications/snowpro-core/ | Capital One, DoorDash, Adobe, Instacart, Square, NBCUniversal, Siemens, Western Union | HIGH
SNF-02 | SnowPro Core | Access Control & Security | ~15% | 90% | Add Tri-Secret Secure example | https://learn.snowflake.com/en/certifications/snowpro-core/ | HIPAA: UnitedHealth, Anthem ¦ SOX: Goldman Sachs, JPMorgan ¦ GDPR: Zalando, Adidas | HIGH
SNF-03 | SnowPro Core | Data Transformation & Movement | ~15% | 92% | Add Snowpipe continuous load | https://learn.snowflake.com/en/certifications/snowpro-core/ | Fivetran (partner), Confluent, Matillion — CDC/ELT ecosystem | MEDIUM
SNF-04 | SnowPro Core | Performance Tuning & Monitoring | ~10% | 75% | Add clustering + Query Profile demo | https://learn.snowflake.com/en/certifications/snowpro-core/ | Lockheed Martin, McKesson — performance tuning for TB-scale DW | MEDIUM
SNF-05 | SnowPro Core | Overview & Connectivity | ~5% | 40% | Build Streamlit + Snowpark app | https://learn.snowflake.com/en/certifications/snowpro-core/ | Snowflake acquired Streamlit ($800M) — official app framework | LOW
DBK-01 | Databricks DE | Lakehouse & Delta Lake | ~20% | 80% | Run local PySpark tests | https://www.databricks.com/learn/certification/data-engineer-associate | Uber (5PB/day), Netflix, Apple, Shell, Comcast, Walgreens, ABN AMRO | CRITICAL
DBK-02 | Databricks DE | ELT & Incremental Processing | ~25% | 75% | Add OPTIMIZE/VACUUM notebook | https://www.databricks.com/learn/certification/data-engineer-associate | Robinhood (real-time trades), DoorDash (live ETAs), Block (fka Square) | CRITICAL
DBK-03 | Databricks DE | Delta Live Tables | ~15% | 75% | Test DLT locally with expectations | https://www.databricks.com/learn/certification/data-engineer-associate | Shell Energy (production DLT), Columbia Sportswear, Rivian | HIGH
DBK-04 | Databricks DE | Data Governance (Unity Catalog) | ~15% | 85% | Add lineage + audit log examples | https://www.databricks.com/learn/certification/data-engineer-associate | HSBC, T-Mobile, JetBlue — Unity Catalog for multi-cloud governance | HIGH
DBK-05 | Databricks DE | Workflows & Production | ~10% | 70% | Add retry + alert config | https://www.databricks.com/learn/certification/data-engineer-associate | Condé Nast, CVS Health, John Deere — production orchestration | MEDIUM
DBT-01 | dbt Analytics Eng | Models & Materializations | ~30% | 95% | Add ephemeral CTE example (done) | https://www.getdbt.com/certifications/analytics-engineer | Spotify, JetBlue, GitLab, Canva, HubSpot, Glossier, Deel, Ramp | CRITICAL
DBT-02 | dbt Analytics Eng | Testing & Documentation | ~25% | 90% | Add custom singular test | https://www.getdbt.com/certifications/analytics-engineer | Notion, Figma, Loom — data testing is #1 quality practice | CRITICAL
DBT-03 | dbt Analytics Eng | Deployment & Advanced | ~20% | 80% | Add dbt docs generate + serve | https://www.getdbt.com/certifications/analytics-engineer | 9,000+ companies use dbt Cloud/Core — 50K+ community members | HIGH

## Python Libraries
PETROVA 300K — PYTHON & LIBRARY REFERENCE
Library | Version | Category | Used In Tasks | Purpose | Install Command | Weekly PyPI Downloads
pyspark | 3.5.3 | Processing | T03,T05,T15-T21 | Distributed data processing (Spark on Python) | pip install pyspark==3.5.3 | 15M+
delta-spark | 3.2.1 | Storage | T03,T05,T15-T21 | Delta Lake ACID tables on Spark | pip install delta-spark==3.2.1 | 2M+
apache-airflow | 2.9.3 | Orchestration | T03,T04,T23 | Workflow orchestration + DAG scheduling | Docker image (pre-installed) | 8M+
dbt-core | 1.8.7 | Transform | T02,T14,T23 | SQL-based data transformation framework | pip install dbt-core==1.8.7 | 4M+
dbt-snowflake | 1.8.4 | Adapter | T02,T14 | dbt adapter for Snowflake warehouse | pip install dbt-snowflake==1.8.4 | 1.5M+
great-expectations | 1.2.0 | Quality | T14,T27 | Data validation and quality checks | pip install great-expectations==1.2.0 | 1.2M+
pandas | 2.2.3 | Analysis | T03,T24 | DataFrame manipulation and analysis | pip install pandas==2.2.3 | 100M+
snowflake-connector-python | 3.12+ | Connector | T06-T13 | Python connectivity to Snowflake | pip install snowflake-connector-python | 5M+
snowflake-snowpark-python | 1.20+ | SDK | T12,T26 | Snowpark DataFrame API for Snowflake | pip install snowflake-snowpark-python | 800K+
streamlit | 1.38+ | Dashboard | T26 | Interactive web app framework | pip install streamlit | 6M+
sqlfluff | 3.1+ | Linting | T29 | SQL linter for CI/CD pipeline | pip install sqlfluff | 2M+
Jinja2 | 3.1+ | Templating | T02 | Template engine (used by dbt internally) | pip install Jinja2 | 150M+
pytest | 8.3+ | Testing | T20 | Python test framework for PySpark tests | pip install pytest | 80M+
chispa | 0.10+ | Testing | T20 | PySpark DataFrame test assertions | pip install chispa | 200K+